## Slide 1: AccelRR8 Consortium NonProfit Professional Networking Service v1
Professional Networking Service Leader
August 12, 2026

## Slide 2: Deliverables Produced During the Review Stage
Reviewing Stage
Analysis Stage
Implementing - MVP Stage

## Slide 3: Service Hypothesis
Reviewing Stage
Analysis Stage
Implementing - MVP Stage
Link to Professional_Networking_v1_Epic-Hypothesis-Statement

## Slide 4: Preliminary Cost Estimates and WSJF
Reviewing Stage
Analysis Stage
Implementing - MVP Stage
Preliminary Cost Estimates | $0: Donation of volunteer time by leaders at no cost to AccelRR8 Consortium Non-Profit $0: Use of LinkedIn and other platforms at no cost to AccelRR8 Consortium Non-Profit
Relative Priority Method: Weighted Shortest Job First (WSJF) Score* | WSJF = 4, which is COST OF DELAY / JOB SIZE = 35 / 8 COST OF DELAY = 11 + 11 + 13 = 35 USER-BUSINESS VALUE = 11 Do subscribers prefer this over other services? 13: the “grow value exponentially at scale” skill is valued What is the revenue impact on the Consortium? 1: the MVP is a free service, though some may donate Are there negative effects if we delay? 20: the Consortium’s other services depend on this one TIME CRITICALITY = 11 Is there a fixed deadline? 1: no fixed deadline Will they wait for us or move to another Solution? 20: AI maturity threatens relevancy What is the current effect on subscriber satisfaction? 13: collaborators want exposure RISK REDUCTION AND/OR OPPORTUNITY ENABLEMENT = 13 Reduces the risk of this or future delivery? 13: critical mass of subscribers is needed for network effects Is there value in the information we receive? 13: willingness of subscribers to engage Enable new business opportunities? 13: subscribers will learn about other Consortium services JOB SIZE = 8; Leaders will need to personally engage 100+ initial subscribers (6 months); Each new subscriber will need to engage 10 additional subscribers (6 months)
*See SAFe WSJF article; scale for each root parameter is 1, 2, 3, 5, 8, 13, 20 (subset of the modified Fibonacci sequence)

## Slide 5: Deliverables Produced During the Analysis Stage
Reviewing Stage
Analysis Stage
Implementing - MVP Stage

## Slide 6: Service Alternatives
Alternative 1: Global, Free, Virtual Professional Network SELECTED | Help enterprising Tech Services leaders make connections and network virtually via free electronic platforms such as LinkedIn
Alternative 2: Local, Fee-based, In-Person Professional Network CONSIDER FOR FUTURE VERSION | (Like Toastmasters) Sponsor and host fee-based events to help enterprising Tech Services leaders make in-person connections and network in localities starting with the Washington, D.C. metro area
Reviewing Stage
Analysis Stage
Implementing - MVP Stage

## Slide 7: Refined Cost Estimates and WSJF
Reviewing Stage
Analysis Stage
Implementing - MVP Stage
Preliminary Cost Estimates | $0: Donation of volunteer time by leaders at no cost to AccelRR8 Consortium Non-Profit $0: Use of LinkedIn and other platforms at no cost to AccelRR8 Consortium Non-Profit
Relative Priority Method: Weighted Shortest Job First (WSJF) Score* | WSJF = 4, which is COST OF DELAY / JOB SIZE = 35 / 8 COST OF DELAY = 11 + 11 + 13 = 35 USER-BUSINESS VALUE = 11 Do subscribers prefer this over other services? 13: the “grow value exponentially at scale” skill is valued What is the revenue impact on the Consortium? 1: the MVP is a free service, though some may donate Are there negative effects if we delay? 20: the Consortium’s other services depend on this one TIME CRITICALITY = 11 Is there a fixed deadline? 1: no fixed deadline Will they wait for us or move to another Solution? 20: AI maturity threatens relevancy What is the current effect on subscriber satisfaction? 13: subscribers want exposure RISK REDUCTION AND/OR OPPORTUNITY ENABLEMENT = 13 Reduces the risk of this or future delivery? 13: critical mass of subscribers is needed for network effects Is there value in the information we receive? 13: willingness of subscribers to engage Enable new business opportunities? 13: subscribers will learn about other Consortium services JOB SIZE = 8; Leaders will need to personally engage 100+ initial subscribers (6 months); Each new subscriber will need to engage 10 additional subscribers (6 months)

## Slide 8: Lean Business Case
Reviewing Stage
Analysis Stage
Implementing - MVP Stage
Link to Professional_Networking_v1_Lean_Business_Case

## Slide 9: Service MVP Component Descriptions
Service Name | Professional Networking
Service Strategy | <3-Horizon Strategy for the Service>
Service Context | <See SAFe Solution Context at this link>
Service Intent | <See SAFe Solution Intent at this link>
Development Kit | <Descriptions of Collateral and Tools used by the Products team to develop the service>
Demand Generation Kit | <Descriptions of Collateral and Tools used by Demand Generation to engage with potential Customers in market segments about the service>
Beneficiaries Engagement Kit | <Descriptions of Collateral and Tools used by Beneficiaries Engagement to engage with specific potential beneficiaries about the service>
Delivery of Service Kit | <Descriptions of Collateral and Tools used by Delivery of Services to engage with beneficiaries about the service>
Reviewing Stage
Analysis Stage
Implementing - MVP Stage

## Slide 10: Deliverables Produced During the Implementing - MVP Stage
Reviewing Stage
Analysis Stage
Implementing - MVP Stage

## Slide 11: Service MVP Component Descriptions
Reviewing Stage
Analysis Stage
Implementing - MVP Stage
Service Name | Professional Networking
Service Strategy | <3-Horizon Strategy for the Service>
Service Context | <See SAFe Solution Context at this link>
Service Intent | <See SAFe Solution Intent at this link>
Development Kit | <Descriptions of Collateral and Tools used by the Products team to develop the service>
Demand Generation Kit | <Descriptions of Collateral and Tools used by Demand Generation to engage with potential Customers in market segments about the service>
Beneficiaries Engagement Kit | <Descriptions of Collateral and Tools used by Beneficiaries Engagement to engage with specific potential beneficiaries about the service>
Delivery of Service Kit | <Descriptions of Collateral and Tools used by Delivery of Services to engage with beneficiaries about the service>