| Funnel Entry Date: February 1, 2024 | Epic Owner: Professional Networking Service Leader |  |  |  | Key Stakeholders: Core Boosters: Board Members, Board Advisors |  |
| --- | --- | --- | --- | --- | --- | --- |
| Epic Description: FOR enterprising leaders involved or interested in the Tech Services industry WHO want to improve their career opportunities and the Tech Services industry’s impact, THE AccelRR8 Consortium Non-Profit’s Professional Networking Service IS AN AI-powered support function connecting a global AccelRR8 professional network THAT helps leaders to network and practice growing value exponentially at scale together, to accelerate success for themselves, their industry, and all humanity. UNLIKE other associations that support professional networks, OUR SERVICE’s own success will be a key proof point of our Consortium’s core premise: due to network effects, value for all subscribers grows exponentially as their numbers grow linearly. |  |  |  |  |  |  |
| Business Outcome Hypothesis: Subscribers: improve their professional network, skills, brand, and career opportunities as measured via survey of subscribers The Tech Services industry: cross-company learning among leaders with scarce talents as measured via survey of collaborators AccelRR8 Consortium: exponential benefits via Market Network Effects (per nfx.com) as measured via survey of subscribers |  |  |  | Leading Indicators: 1000 subscribers - are participating in the AccelRR8 Consortium professional network, and - are Net Promoters of this service as measured via survey of subscribers. |  |  |
| In Scope: - Enterprising Tech Services leaders can join the AccelRR8 Consortium network as subscribers - Global, free, virtual professional network - Helps Tech Services leaders make connections and collaborate virtually via free electronic platforms |  | Out of Scope: - (Like Toastmasters) Individual leaders can join a club / local chapter for a one-time new member fee and a monthly membership fee - (Like ASUG) Organizations can pay an annual fee that covers Professional Networking fees for all employees |  |  |  | Nonfunctional Requirements: - Desirability: all want exponential success, few know how to generate it, and stakeholders like our values and culture - Viability: the Consortium has the required capabilities and isn’t trying to boil the ocean - Sustainability: the core premise (proven accelerators mathematically capable of generating exponential results) is enduring - Performance: the organization’s own success will be a key proof of our core premise, creating a virtuous cycle - Usability: becoming and remaining a subscriber must be incredibly easy |
| Minimum Viable Product (MVP) Features - Enterprising Tech Services leaders simply click to identify as a network subscriber in the AccelRR8 Consortium’s free electronic platform |  |  | Additional Potential Features - Subscribers can learn about, and make connections directly with, each other - Consortium leaders can view analytics about network subscribers |  |  |  |
| Analysis Summary: - MVP desirability, viability, feasibility, and sustainability were verified by the Board of Directors as well as a subset of Advisors and initial subscribers. |  |  |  |  | Go / No-Go: Go! |  |

| Solution Analysis |  |
| --- | --- |
| Which Internal and/or external customers are affected, and how? Our MVP is focused on proving our core premise to establish credibility with our addressable market, which includes leaders and organizations across the Tech Services industry. We will do this by implementing proven accelerators to create Network Effects among a Professional Network of 1,000+ initial subscribers while harnessing Generative Learning and Artificial Intelligence. |  |
| What is the potential impact on solutions, programs and services? As we gain credibility, we will create a virtuous cycle of exponential growth and impact, crossing the chasm from Early Adopters into Mainstream Adoption by leaders and organizations across the Tech Services industry, materially improving the Tech Services industry and helping humanity. |  |
| What is the potential impact on sales, distribution, deployment and support? Demand Generation, Customer Acquisition, and Service Fulfillment for our MVP should be focused on attracting and retaining 1,000+ initial subscribers, all who are Net Promoters of the Consortium’s services and its core premise. As our Service mature beyond MVP, and we find new revenue sources, we will be able to invest in more sophisticated Demand Generation, Beneficiary Engagement, and Delivery of Service activities to further accelerate growth and impact. |  |
| Forecasted Costs |  |
| MVP Cost: Estimate: $10K | Estimated Implementation Cost: Initial estimate: $125K |
| Forecasted Returns |  |
| Type of Return: Leading Indicators: Increasing numbers of subscribers in the Professional Network, tripling every 2-3 years Lagging indicators: Increasing benefit to subscribers, the Tech Services industry, and humanity, as measured by stakeholder surveys |  |

Development Strategy

In-house or Outsourced Development: In-house development: - Service Strategy, Context, Intent, Development Kit, Demand Generation Kit, Beneficiary Engagement Kit, and Delivery of Service Kit Outsourced development: None

Incremental Implementation Strategy: The Product team will take the “Architectural effort precedes business functionality by one or a few iterations” strategy. The Professional Networking Service v1 is a Portfolio-Level Business Epic being developed concurrently with the AccelRR8 Framework open methodology and the AccelRR8 Body of Knowledge Overview MVPs (v1), which in this context are Architectural Epics that support the Business Epic. Click here for details on the “Architectural effort precedes business functionality by one or a few iterations” strategy. © Scaled Agile, Inc.

Sequencing and Dependencies: Required features of the AccelRR8 Framework open methodology and the AccelRR8 Body of Knowledge Overview MVPs (v1) will be developed before they are needed by the Consortium’s Professional Networking Service v1.

Additional Supporting Data

Attachments: See Professional Networking Service Components on Next Slide. These include Service Strategy, Context, Intent, Development Kit, Demand Generation Kit, Customer Acquisition Kit, and Service Fulfillment Kit components.

Other Notes and Comments: Methodologies used to develop the Professional Networking Service MVP include: - The AccelRR8 Framework produced by AccelRR8 LLC - The Scaled Agile Framework produced by Scaled Agile, Inc.